## Sheet1
Project | Facebook Login/Signup QA Project
Release Date | 2025-02-04 |  |  | Project Name (Client Name) | FACEBOOK
Testing Cycle | Feb 17, 2025 - Feb 25, 2025 |  |  | Prepared By | Dalonda Ikhimokpa
UAT Cycle | Feb 25, 2025 - Mar 1, 2025 |  |  | Vesion No | Version 1.0
RISKS:
Details |  | Impact | Mitigation Plan
1: There are 2 "Blocker" defects open |  | High | Fix blocker defect immediately
2: Order purchase test data migration pending |  | Medium | Escalate to database team for migrating test data
EXECUTION SUMMARY
DEFECT SUMMARY

## Sheet2
NEW CHANGES TESTING | Total Cases | Pass | Fail | Incomplete | Blocked | Unexecuted | Run% | Pass% | Fail% | Incomplete% | Blocked% | Unexecuted %
New Product addition | 8 | 5 | 2 | 0 | 1 | 0 | 100% | 62.5% | 25% | 0% | 12.5% | 0%
Search bar changes | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100% | 0% | 0% | 0% | 0%
Account profile picture | 4 | 3 | 0 | 1 | 0 | 0 | 100% | 75% | 0% | 25% | 0% | 0%
G-Pay checkout | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100% | 0% | 0% | 0% | 0%
Mobile-Site improvements | 4 | 2 | 0 | 0 | 0 | 2 | 50% | 100% | 0% | 0% | 0% | 50%
TOTAL | 48 | 42 | 2 | 1 | 1 | 2 | 95.83% | 91.3% | 4.348% | 2.174% | 2.174% | 4.167%
REGRESSION TESTING | Total Cases | Pass | Fail | Incomplete | Blocked | Unexecuted | Run% | Pass% | Fail% | Incomplete% | Blocked% | Unexecuted %
Home Page | 20 | 17 | 3 | 0 | 0 | 0 | 100% | 85% | 15% | 0% | 0% | 0%
Search | 32 | 30 | 2 | 0 | 0 | 0 | 100% | 93.75% | 6.25% | 0% | 0% | 0%
Navigation | 10 | 7 | 2 | 1 | 0 | 0 | 100% | 70% | 20% | 10% | 0% | 0%
Checkout | 40 | 31 | 5 | 0 | 4 | 0 | 100% | 77.5% | 12.5% | 0% | 10% | 0%
Ordering | 12 | 10 | 0 | 0 | 0 | 2 | 83.33% | 100% | 0% | 0% | 0% | 16.67%
Account | 18 | 18 | 0 | 0 | 0 | 0 | 100% | 100% | 0% | 0% | 0% | 0%
Mobile-Site | 30 | 20 | 2 | 0 | 0 | 8 | 73.33% | 90.91% | 9.091% | 0% | 0% | 26.67%
TOTAL | 162 | 133 | 14 | 1 | 4 | 10 | 93.83% | 87.5% | 9.211% | 0.6579% | 2.632% | 6.173%
Project Name (Client Name) | FACEBOOK
Prepared By | Dalonda Ikhimokpa
Vesion No | Version 1.0

## Sheet3
ALL OPEN DEFECTS
Module | Blocker | Critical | Major | Minor | Trivial | Total
Home Page | 1 | 1 | 2 | 0 | 0 | 4
Search | 1 | 0 | 1 | 1 | 1 | 4
Navigation | 0 | 1 | 2 | 3 | 0 | 6
Checkout | 0 | 1 | 1 | 0 | 0 | 2
Ordering | 0 | 0 | 1 | 1 | 0 | 2
Account | 0 | 0 | 3 | 0 | 0 | 3
Mobile-Site | 0 | 0 | 0 | 2 | 3 | 5
Total Unique Issues: | 2 | 3 | 10 | 7 | 4 | 26
DEFECTS BY ASSIGNEE
Components | Blocker | Critical | Major | Minor | Trivial | Total
Dalonda Ikhimokpa | 0 | 0 | 2 | 2 | 0 | 4
Dalonda Ikhimokpa | 0 | 0 | 4 | 1 | 0 | 5
Dalonda Ikhimokpa | 1 | 0 | 1 | 2 | 0 | 4
Dalonda Ikhimokpa | 0 | 1 | 3 | 1 | 0 | 5
Total Unique Issues: | 1 | 1 | 10 | 6 | 0 | 18
DEFECTS VERIFIED
Components | FIXED | REOPENED
Home Page | 0 | 1
Navigation | 3 | 0
Checkout | 0 | 1
Account | 1 | 0
Mobile-Site | 2 | 0
Total Unique Issues: | 6 | 2
Project Name (Client Name) | FACEBOOK
Prepared By | Dalonda Ikhimokpa
Vesion No | Version 1.0